Discussion regarding requirement and documentation for public presentation in August.

The draft document structure was reviewed.

Items to be clarified / amended / provided or added:

- Why are we doing the plan? – (no obligation / discretionary) list headline reasons or a short paragraph.

- What happens without a plan OR what happens with a plan? What differences are made?

- Policies [P] will be written mainly by Feria and will prevent / encourage actions. These will be provisional outlines for the August meeting.

- It was noted that the requirements for development of houses / buildings will be covered under the section on Village Ecology, specifically under 3 policies; Protected Built Heritage, Design and Policy Checklist, Wilder Wallop initiatives.

For the August meeting it is aimed to produce 2 or 3 posters each for each of the 6 headings above and perhaps 12-18 posters, a booklet may be available.

An informal questionnaire might be necessary to gather opinion on whether the public feel the plan is heading in the right direction.  Rather than very specific questions, the survey might ask for comments on the 6 sections - What is:

- Correct

- Missing

- Needs more explanation or detail

- Where might emphasis be placed / is there a preference in terms of  importance

Posters would be designed in format that could be printed out for display, or made into a small booklet, posted online or included in the online survey.

It was discussed that although there is a lot of emphasis regarding the brook, given that the vast majority of Parish land is not bordering  the brook should it feature so highly in the plan? It was concluded that a very high percentage of the residential properties in the Parish were situated around the village centre and therefore the brook was influential on those homes, so it was right to include the section on the subject. However, it was acknowledged that other features around the parish would also be included in whichever policy or section that they affected so that each subject was given consideration and no issue was unduly weighted.

Feria would ask TVBC about protection of the Brook.

Wilder Wallop would be asked to provide some information from the Wallop Brook Farmers relating to conservation projects and areas of scientific interest and the specific action that they intend to take. (Extra question for Feria - should the EA be consulted now or would that wait until reg.14?)

Community spirit docs – It was noticeable that the last public presentation was so well attended and was a good representation of how the community comes together.  More work needs to be done on documenting:

- Protecting existing Community infrastructure.

- Protection of existing employment in the parish.

- Existing community infrastructure.

- Proposals for community spirit. Not specific for pub.

- A list of business and community premises and their uses would be compiled and would be sent to Feria. (KA)

- The list would highlight those that it was thought important to keep. (using 1st survey as evidence.)

Dates for the next public presentation would be considered. GF / RE.  Suggest mid to end August.

A Friday afternoon / evening in a marquee on a green space was suggested. Marquee could be left up over the weekend.  Online questionnaire could run for two weeks afterwards.

Advert for presentation would need to be drafted by 14th July in order to get in the parish Magazine. Also to be on Pump email and Next door and FB.  Copy of the NDP logo would be sent to Feria to be included in the poster. (KA).

Development for the Recreation Ground would be halted as the parish council will take this forward separately. The NDP could specify the requirements for maintaining long term sporting activities in the Village Ecology and Community Spirit sections.   The playing fields had been identified as a LAGS (local area of green space already.)

Timing of writing to landowners whose land had been identified as a possible LAGS was discussed. Feria advised that the owners must be written to prior to going to regulation 14. However there was no requirement to write to them prior to this stage as it would in any case have to be repeated.  A formal letter at this time was not necessary.

The Frequently Asked Questions (FAQ) for Green Spaces would be finished prior to the August presentation.  Feria would update with suggestions and return to the Steering Group. The FAQ would be guidance for SG and Parish Council on how to answer queries, but would not be designed for publication.

A FAQ would be drafted by Feria relating to pros and cons for site allocation. (see minute 85.1.3 from January meeting.) however this was not necessary to be completed before the August presentation.

The mapping System was still not working. This would be remedied, (GF)