NETHER WALLOP PARISH COUNCIL

PROJECT PLAN for the coming year.							Dated: Nov-20

| Project | Objectives | Tasks | Responsibility: | Start Date | Project Duration | Budget Code | Cost | Funding from PC | Grants to be investigated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Website | Comply with Accessibility requirements Improve information and transparency Design a more interesting and engaging website | Review independent audit. Issues & action plan Accessibility statement GDPR review .gov.uk website Sitemap | Clerk + Chairman | Oct-20 | 1 yr | 4180 | £1k ? | a | TBC |
| Council compliance | Ensure council operates lawfully and is seen to do so. | Policies completion / publication External Contract reviews Internal processes reviews. | Clerk | Sep-20 | 2 yrs | n/a | n/a | n/a | n/a |
| Neighbourhood Development Plan | Work with community to produce a plan which protects the important characteristics of the parish from unwanted development. | WG to provide guidance on each part of plan. Consultant to write the plan Public consultations Surveys for feedback | Clerk + NDP Steering Group | Aug-19 | 2 yrs | 5002 | £16k Approx. | a | TVBC – Cllr Grant MCHLG – Locality Local fundraising |
| Safe Travel | Build relationship with Hampshire highways Work with Over Wallop PC. Reduce speeding Provide safer walking routes Improve children’s opportunity to walk to school. | Meetings with HCC Highways Produce evidence of support Contact conflict between residents / farming community Prioritise projects Seek funding Agree feasibility with HCC Schedule implementations. | Clerk + Safe Travel WG | Jul-20 | 2 yrs | 4450 | TBC | r TBC for 2021/22 budget? | HCC – CAF TVBC – CIL TVBC – s.106 |
| Playground Refurb | Provide inspiring and inclusive play equipment Appeal to all age groups Include activities for parents and seniors Improve fitness for all | Decide on a budget Survey children and parents Write a tender spec for contract finder. Apply for grants Fundraise | Clerk + Playground WG | Jan-21 | 2 yrs | 4421 | TBC | r TBC for 2021/22 budget? | Awards4All HCC – CAF TVBC – CIL TVBC – s.106 TBC |
| Communications | Reach every household in the Parish when necessary. Channel feedback to council. Encourage engagement. | Review current methods Survey for preferences Identify handicaps to implementing Identify costs | Clerk + ? | Nov-20 | 1 yr | TBC | TBC | r TBC for 2021/22 budget? | TBC |
| Climate Emergency | ? | ? | ? | TBC | 2 yr + | TBC | TBC | r TBC for 2021/22 budget? | TBC |
| Covid-19 in the community | ? | ? | ? | TBC | 1 yr | TBC | TBC | r TBC for 2021/22 budget? | TBC |
| Renewable energy projects | ? | ? | ? | TBC | 2 yr + | TBC | TBC | r TBC for 2021/22 budget? | TBC |